## Slide 1: Class 2DC2DD Group 21 SPRINT 2
Group members:
Bárbara Pinto (1191507)
Carlos Dias (1200991)
Cristóvão Sampaio (1201029)
Miguel Silva (1201045)
Martim Maciel (1201154)

## Slide 2: Sprint planning – Sprint 2
SPRINT BACKLOG | 
Number of stories | 11
Number of bugs | 00
Number of tasks | 37
Number of Management Tasks | 04
Number of team members | Planned: 5 Actual: 5
Total planned estimation vs execution | Planned hours: 10w 3h Executed hours: ~10w
Planned Start Date: Nov. 15th Real Start Date: Nov. 15th
Planned Finished Date: Dec. 3rd Real Finish Date: Dec. 5th

## Slide 3: Sprint planning
Assignment US | Commited? | Todo | Doing | Testing | Done | Blocked
US201 | Yes |  |  |  | x | 
US202 | Yes |  |  |  | x | 
US203 | Yes |  |  |  | x | 
US204 | Yes |  |  |  | x | 
US205 | Yes |  |  |  | x | 
US206 | Yes |  |  |  | x | 
US207 | Yes |  |  |  | x | 
US208 | Yes |  |  |  | x | 
US209 | Yes |  |  |  | x | 
US210 | Yes |  |  |  | x | pending client approval
US111 | Yes |  | database automation |  | x | 

## Slide 4: Sprint Execution
Issues | Sprint Backlog (a) | Added issues during sprint (b) | Closed issues from initial planning (c) | Closed issues from added ones (d) | Issues not closed (e) | % Execution | 
 |  |  |  |  |  | Planned (c/a) | Total (c+d)/(a+b)
Number of stories (I) | 11 | 0 | 11 | 0 | 0 | 100 | 100
Number of bugs (II) | 39 | 114 | 0 | 89 | 25 | 0 | 58
Number of tasks (III) | 36 | 1 | 36 | 1 | 0 | 100 | 100
TOTAL | 86 | 115 | 47 | 90 | 25 | 55 | 68
Total Estimate | 10w 3h |  |  |  |  |  | 

## Slide 5: Work by team member
Chart: Commit effort
| 1191507 | 1200991 | 1201029 | 1201045 | 1201154
no.commits / no. issues | 18 | 26.5 | 21 | 19 | 13.5

## Slide 6: Work by type
Chart: Issues per component
| ESINF | BDDAD | LAPR3
Componente | 0.13333 | 0.6 | 0.26667
Notes: “Era interessantes inventarem componentes, tais como gestão a 15%”

## Slide 7: Sprint Burndown Chart
Print do JIRA após fecho da sprint
Chart: Closed issues
| dia 1 | dia 2 | dia 3 | dia 4 | dia 5 | dia 6 | dia 7 | dia 8 | dia 9 | dia 10 | dia 11 | dia 12 | dia 13 | dia 14 | dia 15 | dia 16 | dia 17 | dia 18 | dia 19 | dia 20 | dia 21
Sprint2 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 9 | 8 | 8 | 8 | 8 | 5 | 2 | 1 | 0
Sprint1 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 13 | 12 | 12 | 7 | 2 | 1 | 1

## Slide 8: Sprint Review
Date: 05 nov. 2021
Main conclusions
From the scrum team work:
Good teamwork distribution for the available time.
Lack of information and clarifications from client. Team must study the business model closely and develop adequate solutions.
Daily progress must be monitored more closely.
From implemented functionalities:
Database connection can be very unstable, especially in remote servers. Mock tests were developed to assure successful compilation while keeping project integrity.
The new approach to cargo manifest handling (full and partial) was implemented manually but requires automation at the database level.
Data loading and querying were successfully implemented and tested.

## Slide 9: Sprint Retrospective
Date: 05 nov. 2021
What went well?
Good User Story distribution
User Story dependencies were well determined
Excellent team work and shared knowledge
Faster task execution time, as the result of the solid foundation developed in Sprint 1 and previous experience.
What went wrong?
Development began late in the sprint (but earlier than previous sprint) due to presentations and evaluation moments in class.
Late or insufficient clarifications from the client and the technical team.
JIRA management issues that blocked the team from accurately registering user story estimation and daily progress.
Database crashing/unavailable
What we’ve learned?
User Stories must be more carefully estimated in Sprint 3 due to the high work load
Database connection must be stabilized and some data handling must be automated

## Slide 10: Sprint Retrospective
Date: 05 nov. 2021
Action items:
Project Management:
Justify user story estimations
Register daily progress in every commit
Add client clarifications and business model analysis to each User Story in sprint backlog
Functionalities:
Implement database automation at the cargo manifest creation level
Improve bootstrap script
Improve tests related to database connection

## Slide 11: Team performance metrics
Chart: 
| Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4
Code coverage (%) | 97.2 | 94 | 0 | 0
Mutation coverage (%) | 85.3 | 83.4 | 0 | 0
Duplicated code (%) | 0 | 0 | 0 | 0
Technical debt (hours) | 24 | 48 | 0 | 0
Notes: “Registar os vários burndowns de várias sprints para ver se há padrões”, “ Ver se a velocidade tá a aumentar, diminuir, ou é constante”